## Torque Budget
6-DoF Arm — Gravity Torque Budget v2 (elbow-mounted forearm roll)
Joint order (base to tool): J1 yaw·z, J2 shoulder pitch·x, J3 elbow pitch·x, J4 forearm roll·y AT ELBOW, J5 wrist pitch·x, J6 tool roll·y. Blue cells = inputs. Worst case: arm horizontal.
GEOMETRY (total reach = shoulder pitch axis to tool center point)
L1 — upper arm (shoulder pitch to elbow pitch axis) | 0.25 | m
L2 — forearm (elbow pitch to wrist pitch axis) | 0.07 | m
L3 — wrist pitch axis to TCP | 0.08 | m | [5 empty] | Payload CG assumed at TCP
d4 — J4 roll actuator CG offset distal of elbow | 0.03 | m | [5 empty] | How far past the elbow pitch axis the J4 motor sits
Total reach | 0.4 | m | [5 empty] | Target: 0.400 m as decided
MASSES
J3 elbow pitch actuator (mj5208 + r4.11 + cycloidal) | 0.89 | kg | [5 empty] | Body mounted on upper-arm side of the joint
J4 forearm roll actuator (small motor + driver + housing) | 0.12 | kg | [5 empty] | e.g. gimbal motor ~90 g + moteus-c1 ~9 g + printed reducer/housing
Wrist cluster — J5 + J6 only (2 actuators + structure) | 0.22 | kg | [5 empty] | Was 0.35 kg with a 3-axis wrist — this is the payoff of the move
Gripper (actuator + jaws) | 0.15 | kg | [5 empty] | Keep under ~0.2 kg
Payload (design requirement) | 0.2 | kg | [5 empty] | 500 g spec
Upper arm link (CF tube + clamps, CG at L1/2) | 0.06 | kg
Forearm link (CF tube + clamps, CG at L1 + L2/2) | 0.06 | kg | [5 empty] | Slightly heavier in practice: it must carry the J4 rotating interface
CONSTANTS & DESIGN FACTORS
Gravitational acceleration g | 9.81 | m/s²
Safety factor on continuous torque | 1.5 | [6 empty] | Covers cycloidal friction variation, print quality, dynamic loads while carrying payload
ACTUATOR PARAMETERS
mj5208 continuous torque | 0.3 | Nm | [5 empty] | Your figure, w/ heat spreader @ 24 V. Verify at thermal steady state on the bench.
mj5208 peak torque | 1.7 | Nm | [5 empty] | mjbots spec; transient only
mj5208 speed at continuous rating | 240 | rpm | [5 empty] | No-load speed is much higher; peak joint speed exceeds this
Cycloidal gearbox efficiency | 0.65 | - | [5 empty] | ASSUMPTION — printed cycloidals range ~0.60–0.90. Measure and update.
Gear ratio — J1 base yaw | 15 | :1 | [5 empty] | Gravity load ~0; existing 15:1 design is fine
Gear ratio — J2 shoulder pitch | 30 | :1 | [5 empty] | 15:1 fails the budget below even with the lighter wrist
Gear ratio — J3 elbow pitch | 15 | :1 | [5 empty] | Existing 15:1 design
Small motor continuous torque (J4–J6) | 0.2 | Nm | [5 empty] | e.g. GM4108-class gimbal + moteus-c1. Edit if using a smart servo instead.
Small motor gear ratio (J4–J6) | 8 | :1 | [5 empty] | Printed planetary; J4 wants a hollow bore or belt offset for wiring
Small motor gear efficiency | 0.85 | -
COMPONENT GRAVITY TORQUES — ARM HORIZONTAL (worst case)
Component | Mass (kg) |  | CG dist from shoulder (m) | CG dist from elbow (m) | τ about shoulder (Nm) | τ about elbow (Nm)
Upper arm link | 0.06 |  | 0.125 | — | 0.073575 | 0
J3 elbow pitch actuator | 0.89 |  | 0.25 | — | 2.1827 | 0
J4 forearm roll actuator (at elbow) | 0.12 |  | 0.28 | 0.03 | 0.32962 | 0.035316
Forearm link | 0.06 |  | 0.285 | 0.035 | 0.16775 | 0.020601
Wrist cluster (J5 + J6) | 0.22 |  | 0.32 | 0.07 | 0.69062 | 0.15107
Gripper | 0.15 |  | 0.36 | 0.11 | 0.52974 | 0.16187
Payload @ TCP | 0.2 |  | 0.4 | 0.15 | 0.7848 | 0.2943
TOTAL static gravity torque |  |  |  |  | 4.7588 | 0.66316
DISTAL AXIS GRAVITY TORQUES
Gripper about wrist pitch axis (CG at L3/2) |  |  |  |  | 0.05886
Payload about wrist pitch axis (at L3) |  |  |  |  | 0.15696
TOTAL — J5 wrist pitch requirement |  |  |  |  | 0.21582 |  |  | J4 forearm roll sees the SAME worst case: with the wrist pitched 90°, the gripper + payload hang off the roll axis on the same lever arms
JOINT SIZING SUMMARY
Joint | Required cont. τ (Nm) | Req. × SF (Nm) | Ratio | Available cont. τ (Nm) | Margin (avail / req×SF) | Status | Peak τ avail (Nm) | Output speed (°/s)
J1 base yaw · z (mj5208) | 0.5 | 0.75 | 15 | 2.925 | 3.9 | PASS | 16.575 | 96
J2 shoulder pitch · x (mj5208) | 4.7588 | 7.1382 | 30 | 5.85 | 0.81953 | UNDERSIZED | 33.15 | 48
J3 elbow pitch · x (mj5208) | 0.66316 | 0.99473 | 15 | 2.925 | 2.9405 | PASS | 16.575 | 96
J4 forearm roll · y (small motor) | 0.21582 | 0.32373 | 8 | 1.36 | 4.201 | PASS | —
J5 wrist pitch · x (small motor) | 0.21582 | 0.32373 | 8 | 1.36 | 4.201 | PASS | —
J6 tool roll · y (small motor) | 0.15 | 0.225 | 8 | 1.36 | 6.0444 | PASS | —
Notes:
• J1 required torque is an input: it carries ~zero gravity torque and is sized by friction + acceleration of full-arm inertia.
• J6 required torque is an input: gravity torque about the tool roll axis is only the payload CG offset from that axis; sized mainly for grasp disturbances.
• J4 worst case = wrist pitched 90° with payload (same lever arms as J5), so both use the same requirement and actuator for commonality.
• vs the 3-axis-wrist version: shoulder requirement drops ~0.2 Nm and elbow ~0.15 Nm from moving one actuator's mass off the forearm tip.
• Route wiring for J5/J6/gripper through or past J4: limit J4 travel (±~270°) with a cable service loop, or design a hollow-bore reducer. No slip rings.
• After the single-joint bench test, replace the 0.80 cycloidal efficiency assumption with the measured value.

## Timeline
Build Timeline — 6-DoF Arm for ML/RL Experiments (v2 architecture)
Assumes evenings/weekends pace alongside full-time work. Phases overlap deliberately — order long-lead parts early. Durations are estimates; the exit criterion is what matters.
# | Phase | Weeks | Key tasks & exit criteria | Notes | Recommendations
1 | Finalize budget & architecture | 1–2 | Fill this workbook with real masses; lock reach (400 mm), z-x-x-y-x-y joint layout, J2 ratio, J4–J6 actuator choice. Exit: every joint row reads PASS. | J4 and J5 share a requirement (~0.45 Nm) — use the identical actuator + reducer for both, and ideally J6 too, for spare-parts commonality. | Order long-lead parts NOW: mj5208s, r4.11s, heat spreaders, CAN-FD USB adapter, CF tube, bearings, small motors + moteus-c1s. Shipping is your critical path.
2 | Single-joint bench test (mj5208 + 15:1 cycloidal) | 2–3 | Rig one joint with a weighted lever. Measure: continuous torque at thermal steady state (20+ min hold, log winding temp via moteus telemetry), gearbox efficiency, backlash, friction. Exit: measured values entered into the Torque Budget sheet. | Validates the two biggest assumptions (0.3 Nm continuous, 0.80 efficiency). Printed cycloidal efficiency varies 0.60–0.90 with print quality and grease. | Log via moteus telemetry — the same friction/backlash data becomes your sim parameters later. Compare PETG vs PLA cycloidal discs for wear while you're at it.
3 | J4 roll joint + wrist prototype | 3–5 | Build the J4 forearm roll joint first — it's the novel one: small motor + moteus-c1 + hollow-bore (or belt-offset) reducer, with the distal wiring harness passing through. Then the 2-axis wrist. Exit: J4 holds 0.45 Nm with wiring routed and ±270° travel limits set; wrist cluster weighed at ≤ budget. | The rotating wire pass-through is the highest-risk detail of this architecture. Prove it before committing to the forearm design. Set voltage_mode_control if gimbal current-sense torque is noisy. | Give the harness a generous helical service loop through the J4 bore and enforce soft travel limits in moteus config. If J4 drags on, fall back to a smart-servo wrist and add the roll later.
4 | Full arm CAD | 4–7 | Model complete arm incl. the J4 rotating interface, wiring routes, controller mounting, service loops. Pull mass properties into the Torque Budget sheet and iterate. Exit: budget still PASS with CAD masses + 10% contingency. | Split-clamp CF tube fittings (bolted, not glued) let you change link lengths after testing. Bearings, not printed bores, on all moment-loaded interfaces — especially the J4 output, which sees the full forearm bending moment. | Design so J4, J5, J6 axes intersect at one wrist-center point — that preserves closed-form IK (Pieper's condition). Add joint hard-stops so a runaway policy can't self-collide at full torque.
5 | Electronics & power integration | 6–8 | 24 V PSU (~10–15 A), power distribution, daisy-chained CAN-FD through all 6 controllers + gripper, termination, physical e-stop cutting motor power. Exit: all nodes enumerate; 100 Hz command/telemetry loop stable from Jetson or PC. | One mjcanfd-usb-1x handles the whole chain — r4.11 and c1 share the same bus, firmware, and API. Keep Jetson logic power separate from motor power. | Add a bus voltage monitor: regen from decelerating joints pumps the rail up. Configure moteus flux braking before the first fast motion.
6 | Fabrication & assembly | 7–9 | Print structure (PETG for structural/heat-adjacent parts), cut tubes, assemble, torque-check fasteners. Exit: arm holds a static pose under closed-loop control without thermal throttling. | Expect 2–3 reprints of joint housings; that's normal. Anneal or thicken parts near motor heat spreaders. | Assemble and test joint-by-joint from the base up — much easier to isolate mechanical vs firmware issues.
7 | Calibration & controller tuning | 8–10 | Per-joint encoder calibration, direction/limit config, position + velocity + torque tuning, gravity compensation feedforward from this sheet's mass model. Exit: arm tracks smooth trajectories with 500 g payload, no overheating over a 15-min cycle. | Gravity comp is nearly free — the mass/CG model is already in the Torque Budget sheet. It dramatically improves teleop feel and cuts steady-state heating. | Add output-side AS5047 encoders (r4.11 aux SPI) on J2/J3 if cycloidal backlash exceeds ~0.5° — joint-side truth matters for RL state.
8 | Software: driver + LeRobot integration | 9–11 | Python moteus driver wrapped in a LeRobot robot class; camera integration; teleop (leader arm, spacemouse, or keyboard). Exit: record a LeRobot dataset end-to-end with synced camera + joint states. | You've already debugged the hard parts on the YAM arm — record-loop FPS, camera sync, and rerun latency lessons transfer directly. | Run policy/teleop at 30–50 Hz; let moteus onboard loops handle high-rate control. Keep camera reads asynchronous from the record loop from day one this time.
9 | Sim model & system ID | 10–12 | Build URDF/MJCF from CAD; import to MuJoCo (and Isaac Lab for GPU sim); fit joint friction, damping, backlash from Phase 2/7 logs. Exit: sim joint step responses match hardware within ~10–15%. | Printed cycloidal friction is the dominant sim-to-real gap — it's load-dependent, so fit at several torque levels. Note the wrist singularity at J5 = 0 (J4 and J6 axes align) — joint-space policies don't care, Cartesian teleop will. | Export CAD with simplified collision meshes now; retrofitting them later is painful. Randomize friction/backlash in training rather than chasing a perfect fit.
10 | First learning experiments | 12+ | Baseline tasks: reach, pick-place, peg-in-hole. Start with imitation learning (ACT/diffusion policy on teleop demos), then RL fine-tuning in sim. | Train on the gaming PC (RAM/GPU matter for training); Jetson for deployment/inference only. | Start with IL from ~50 teleop demos before any RL — it validates the whole platform with far less debugging surface than sim-to-real RL.

## BOM
# | BOM Level | Item | Qty | Price per Unit | Specifications | link | Ordered On | # of Packs Ordered | Shipping/Tax | Total Cost
1 | 1 | 6-DoF Robotic Arm | 1 |  | 6-DOF Robotic Arm |  |  |  |  | 1390.51
1.1 | 2 | Proximal joint actuation — J1–J3 (mj5208 + printed cycloidal) | [7 empty] | 960.84
1.1.1 | 3 | mj5208 brushless motor | 2 | 74 | Drives J1 & J2 | Here | 2026-08-03 | 2/2 | 2.4425 | 148
1.1.2 | 3 | moteus r4.11 controller | 2 | 94 | J1 & J2 | Here | 2026-08-03 | 2/2 | 2.4425 | 188
1.1.3 | 3 | moteus r4.11 developer kit | 1 | 219 | J3 motor + controller bundle | Here | 2026-07-10 | 1/1 | 2.4425 | 219
1.1.4 | 3 | moteus r4 heat spreader | 3 | 29 | One per mj5208 joint (J1–J3) | Here | 7/10/2026 8/3/2026 | 1/3 2/3 | 11.07 | 87
1.1.5 | 3 | SteadyWin GIM3505-8 planetary reducer motor | 2 | 65 | J4, J5, J6 (V1.0 with encoder) | Here | 2026-07-10 | 3/3 | 30 | 130
1.1.6 | 3 | moteus-c1 controller | 2 | 69 | J4, J5, J6 | Here | 2026-08-03 | 3/3 | 2.4425 | 138
1.2 | 2 | Cycloidal gearbox — 30:1 (J2 shoulder) | 1 | Price/Pack | [5 empty] | 135.48
1.2.1 | 3 | Roller Pin | 39 | 7.21 | Ø5mm x 30mm (50 pcs) | Here | 2026-07-27 | 1 | 7.68 | 7.21
1.2.2 | 3 | Roller/Output Bearings | 78 | 12.99 | ID 5mm x OD 10mm x 4mm (30 pcs) | Here | 2026-07-27 | 3 |  | 38.97
1.2.3 | 3 | Camshaft Bearings | 4 | 9.99 | ID 15mm x OD 28mm x 7mm (8 pcs) | Here | 2026-07-27 | 1 |  | 9.99
1.2.4 | 3 | Input/Output Flanged Bearings | 2 | 9.79 | ID 50mm x OD 65mm x 7mm (2 pcs) | Here | 2026-07-27 | 1 |  | 9.79
1.2.5 | 3 | M5 Heat Set Threaded Inserts | 17 | 6.99 | M5 x Ø10mm x 7mm (50 pcs) | Here | 2026-07-27 | 1 |  | 6.99
1.2.6 | 3 | M2.5 Heat Set Threaded Inserts | 5 | 8.99 | M2.5 x Ø3.5mm x 4mm (100 pcs) | Here | 2026-07-27 | 1 |  | 8.99
1.2.7 | 3 | Shoulder bolts M5 | 8 | 7.79 | M5x0.8 around 64mm in total length (4 pcs) | Here | 2026-07-27 | 2 |  | 15.58
1.2.8 | 3 | M5 Screw | 9 | 22.99 | M5x0.8 x 13mm length | Here | 2026-07-27 | 1 |  | 22.99
1.2.9 | 3 | M3 Screw | 7 |  | M3 x 4mm length (4) 6mm length (3)
1.2.10 | 3 | M2.5 Screw | 4 |  | M2.5 x 4mm length |  | Already Have
1.2.11 | 3 | M2.5 Set Screw | 1 | 7.29 | M2.5 x 4mm length (50 pieces) | Here | 2026-07-27 | 1 |  | 7.29
1.2.12 | 3 | Hex Shaft | 1 | 21.45 | 5mm x 51mm (4 pcs 400mm in length each) | Here | Already Have
1.2.13 | 3 | 30-Ouput Flange | 1 |  | 3D Printed Parts
1.2.14 | 3 | 30-Input Flange | 1
1.2.15 | 3 | 30-Thin Spacer | 78
1.2.16 | 3 | 30-Thick Spacer | 39
1.2.17 | 3 | 30-Cycloidal Disk | 2
1.2.18 | 3 | 30-Eccentric Cam | 2
1.2.19 | 3 | 30-Centered Cam | 1
1.2.20 | 3 | 30-Input Cam | 1
1.2.21 | 3 | 30-Motor Housing | 1
1.2.22 | 3 | 30-Mid Wall | 1
1.2.23 | 3 | 30-Output Wall | 1
1.2.24 | 3 | 30-Output Wall | 1
1.2.25 | 3 | 30-Coupler | 1
1.3 | 2 | Cycloidal gearbox — 15:1 (J1, J3) | 2 | Price/Pack | [5 empty] | 103.49
1.3.1 | 3 | Roller Pin | 22 | 7.21 | Ø5mm x 30mm (50 pcs) | Here | 2026-08-03 | 1 | 5.87 | 7.21
1.3.2 | 3 | Roller/Output Bearings | 44 | 12.99 | ID 5mm x OD 10mm x 4mm (30 pcs) Purchase 3 packs for two 15:1 gearboxes | Here | 2026-08-03 | 3 |  | 38.97
1.3.3 | 3 | Camshaft Bearings | 4 | 8.09 | ID 10mm x OD 15mm x 4mm (10 pcs) Purchase 1 pack for two 15:1 gearboxes | Here | 2026-08-03 | 1 |  | 8.09
1.3.4 | 3 | Input/Output Flanged Bearings | 2 | 9.99 | ID 40mm x OD 52mm x 7mm (4 pcs) Purchase 1 pack for two 15:1 gearboxes | Here | 2026-08-03 | 1 |  | 9.99
1.3.5 | 3 | M5 Heat Set Threaded Inserts | 15 | 6.99 | M5 x Ø10mm x 7mm (50 pcs) | Here | Already have from 30:1 |  |  | 0
1.3.6 | 3 | M2.5 Heat Set Threaded Inserts | 5 | 8.99 | M2.5 x Ø3.5mm x 4mm (100 pcs) | Here | Already have from 30:1 |  |  | 0
1.3.7 | 3 | Shoulder bolts M5 | 6 | 7.79 | M5x0.8 around 54mm in total length (4 pcs) Purchase 3 packs for two 15:1 gearboxes | Here | 2026-08-03 | 3 |  | 23.37
1.3.8 | 3 | M5 Screw | 9 | 22.99 | M5x0.8 x 10mm length | Here | Already have from 30:1 |  |  | 0
1.3.9 | 3 | M3 Screw | 7 |  | M3 x 4mm length (4) 6mm length (3)
1.3.10 | 3 | M2.5 Screw | 4 | 9.99 | M2.5 x 4mm length | Here | 2026-08-03 | 1 |  | 9.99
1.3.11 | 3 | M2.5 Set Screw | 1 | 7.29 | M2.5 x 4mm length (50 pieces) | Here | Already Have from 30:1 |  |  | 0
1.3.12 | 3 | Hex Shaft | 1 | 21.45 | 5mm x 56mm (4 pcs 400mm in length each) | Here | Already Have
1.3.13 | 3 | 15-Ouput Flange | 1 |  | 3D Printed Parts Need to 2x prints for two 15:1 gearboxes
1.3.14 | 3 | 15-Input Flange | 1
1.3.15 | 3 | 15-Thin Spacer | 44
1.3.16 | 3 | 15-Thick Spacer | 22
1.3.17 | 3 | 15-Cycloidal Disk | 2
1.3.18 | 3 | 15-Eccentric Cam | 2
1.3.19 | 3 | 15-Centered Cam | 1
1.3.20 | 3 | 15-Input Cam | 1
1.3.21 | 3 | 15-Motor Housing | 1
1.3.22 | 3 | 15-Mid Wall | 1
1.3.23 | 3 | 15-Output Wall | 1
1.3.24 | 3 | 15-Output Wall | 1
1.3.25 | 3 | 15-Coupler | 1
1.3.25 | 3 | 15-camshaft_spacer | 3
1.4 | 3 | Misc |  | Price/Pack | [5 empty] | 190.7
1.3.1 | 4 | 16 AWG Silicone Wire Red Black | 1 | 7.21 | 10ft Stranded Tinned Copper Wire | Here | 2026-08-03 | 1 | 5.87 | 7.21
1.3.2 | 4 | 2pcs Carbon Fiber Tube | 1 | 24.33 | 25mmx23mmx420mm 3K roll Wrapped Twill Matte Finish | Here | 2026-09-06 | 1 |  | 24.33
1.3.3 | 4 | GH1.25 Connectors and Crimp Terminal kit | 1 | 10.99 | Compatible with JST GH Connectors Plugs 1.25mm Pitch | Here | 2026-09-08 | 1 |  | 10.99
1.3.4 | 4 | Camera for gripper | 1 | 31.99 | Arducam 5MP Wide Angle USB Camera for Computer, 1/4" CMOS OV5648 Mini UVC USB2.0 Video Webcam with Microphone, with 3.3ft/1m Cable | Here | 2026-09-08 | 1 |  | 31.99
1.3.5 | 4 | Power supply Y-splitter cables | 1 | 9.99 | Frienda 20 Pairs XT30 Connectors Male Female, Gold Plated RC Lipo Battery | Here | 2026-09-08 | 1 |  | 9.99
1.3.6 | 4 | Servo controller for gripper | 1 | 12.99 | Waveshare Serial Bus Servo Driver Board, Integrates Servo Power Supply and Control Circuit, Applicable for ST/SC Series Serial Bus Servos, Small in Size, Easy to Integrate | Here | 2026-09-08 | 1 |  | 12.99
1.3.7 | 4 | Servo Wiring | 1 | 9.59 | (6PCS) 5264-3PIN Servo Cable (6PCS), for ST/SC/CF Servos, 900MM / 90CM Length | Here | 2026-09-10 | 1 |  | 9.59
1.3.8 | 4 | Servo | 1 | 30.9 | waveshare 30KG High Precision and Torque Servo Motor Metal Gear ST3215 Programmable 360° Magnetic Encoder Serial Bus Servo for Robot Project,Two-Way Feedback, Servo/Motor Mode Switchable | Here | 2026-09-10 | 1 |  | 30.9
1.3.9 | 4 | Servo Set Screws | 1 | 5.29 | M3 x 4mm 304 Stainless Steel | Here | 2026-09-12 | 1 |  | 5.29
1.3.10 | 4 | Servo Flanged Bearings | 1 | 8.58 | 6x10x3mm Miniature Flanged Bearings, | Here | 2026-09-12 | 1 |  | 8.58
1.3.11 | 4 | M2 screw set | 1 | 9.99 | 1600Pcs M2 Screws,M2*4/6/8/10/12/16/20/25mm Screw kit | Here | 2026-09-13 | 1 |  | 9.99
1.3.12 | 4 | Carbon fiber tube | 1 | 9.99 | Carbon Fiber Round Tube 6mm x 4mm x 200mm | Here | 2026-09-14 | 1 |  | 9.99
1.3.13 | 4 | Adjustable Voltage Regulator | 1 | 12.99 | Servo power supply | Here |  | 1 |  | 12.99